## Slide 1
JIAC #1: Clean Tech Advance
This project is funded by EDA ($1M), ETA ($1M) and SBA ($150k)
Portland, Oregon
Counties: Clackamas, Multnomah & Washington (Oregon); Clark & Cowlitz (Washington)
Vision and Collaboration
Project Plan and Objectives
Project Activities / Events
Cluster/Business Sector Description
Outcomes
Lessons Learned from
Overcoming Challenges
EDA (PDC) Jared Wiener,
wienerj@pdc.us
ETA (WSI) Jesse Aronson, jaronson@worksystems.org
SBA (OMEN) Emily Leuning, emily@omenetwork.org
Simplify project and focus efforts on a couple key deliverables
Establish expectations of subs and ensure they deliver on them
Complexity of project means it will take significant time & effort to get underway
Disconnect between industry expectations on delivery and government’s ability to iterate and make changes
Increased collaboration amongst agency partners/ team members
Provided networking opportunities for cluster companies and employees resulting in partnerships and jobs
Market research provided mostly to disadvantaged and underserved businesses
Lessons learned on industry – public – private partnerships as well as tangible success in some instances.
59 individuals trained and obtained Clean Tech related employment.
EDA: Supporting industry growth in the clean tech sector with supply chain activities, technical and business support for small and mid-sized clean tech businesses.
ETA: Worksystems and America’s Job Centers, are providing training and employment services to 92 unemployed and 50 current workers. Executive training is underway for firms looking to enter or grow in the clean tech market.
SBA: Oregon Microenterprise Network is providing market research to 25 businesses .
Unite: 1) clean tech, 2) research and commercialization and 3) advanced manufacturing opportunities.
Anchor businesses – particularly micro-, small-, and medium-sized business at the center of training commercialization opportunities.
Equip the workforce with in-demand skills.
Changes Since October 2011
Staff turnover by primes as well as subs has changed working dynamics.
Opportunities on better aligning local public purchasing of clean tech products and services has provided opportunities on supply chain development.
Success of We Build Green Cities international branding effort has provided opportunities for all economic development components.
Macro-level economic growth and trends toward cleaner technology has enhanced opportunities.
The Clean Tech Advance Initiative is a bi-state partnership of more than 20 organizations to support innovation and job creation in the Clean Tech and Advanced Manufacturing Industry Clusters.
Clean Tech includes a broad category of innovative products, processes and services that share a common thread in applying technology or innovations to produce efficiency (including the reduction of waste).
Goals and Impacts
Year 1 (Achieved)
Established sub grant contracts
Began market research, worker training and supply chain work
Built local organizational partnerships
Year 2 (Achieved)
Increased market research and worker training efforts
Continued supply chain work
Built partnerships to provide technical and business research that support commercialization of technologies.
Year 3 (In Progress)
Continue efforts of year 1 and 2.
Complete market research efforts
Develop partnership to provide product certification for new technologies entering clean tech marketplace.
This effort is oriented to capitalize on Portland’s global presence as a green city and a clean tech haven, while supporting our legacy manufacturing industry with new opportunities .
EDA funds the growth of traded sector businesses and overall industry growth in the clean tech sector including allowing established firms to enter.
ETA supports training of workers for the clean tech industry from traditional degree programs to On-the-Job Training to executive level business development workshops.
SBA funds the growth of small and early stage businesses of diverse backgrounds toe enter/succeed in the clean tech marketplace.
Clean tech and advanced manufacturing sectors will continue to be focus throughout region and states.
Continued partnership for agency leads
Region received funding from JIAC #3 for advanced manufacturing sector
Ability to leverage partnership for deployment in other key industry clusters (Athletic & Outdoor and/or Software)
Continuity Plans
Team Contact Information